## Sheet1
Date | Milestone Client | Milestone Server | Milestone Game
2016-03-04 | Networking Connection server/client | Networking Connection server/client | Initial cards lists/UI design finish
2016-03-11 | UI layout Finished, Basic Networking Commands | Basic Networking Commands, AI games | Establish Network Commands
2016-03-18 | Minimal Viable Product | Minimal Viable Product | Music/Sound
2016-03-25 | Receive other player data | Multiple Game Instances w/ Multiple Players | Profile art
2016-04-01 | Lobby search | Lobby Search | UI art finished
2016-04-08 | Chat | Chat | Web host testing
2016-04-15 | UI Finished,Final Testing Phase | Final Testing Phase | Card list finalized, User Testing
2016-04-22 | Final Finishing touches | Final Finishing touches | Final Finishing touches